## Slide 1
AMAZON OPERATIONS · WEEKLY REVIEW
Presented by Zarlish
Cadence week 1 · Friday review
PPC
Week of September 28 to October 2
CooLinens Cooling Pillowcase goes live on Amazon today with its PPC launch. Bamboo ranking plans for B4 and B6 are final and wait on three sign-offs. Prime Big Deal Days on 6–7 Oct is the first test of the week ahead.
6
Workstreams
3
Delivered
2
In progress
1
At risk
0 of 4
Cadence logged

## Slide 2
PPC · ALL BRANDS · WEEK OF SEPTEMBER 28 TO OCTOBER 2
Progress versus plan
01
PPC · Sep 28–Oct 2
WORKSTREAM | WHAT WAS PLANNED | WHAT ACTUALLY HAPPENED | STATUS
Nine-product audit cycle All three · weekly cycle · P0 | All nine audited, reviewed by all three and executed through the app. Bamboo Monday, the rest Tuesday | Feedback posted on six: B4, B6, S4, S6, Satin Fitted, SS-S4. The remaining three, Cooling Sheets 4-PC, Bamboo Fitted and Cooling Fitted, are being completed today | 6 of 9 · 3 today
Engine corrections & feedback Joseph with PPC review · P0 | One consolidated note per product to Joseph, engine fixed and the audits re-run on the corrections | B4 and B6 corrections applied and re-audited 29 Sep, the first clean 218/218 pass. Engine feedback doc and issue register delivered today | Done
Bamboo ranking push (B4, B6) Shayan T with Joseph · P0 | One ranking plan per listing, matched to Joseph's keyword story and plan of attack, before the pushes start | Plan of attack shared 1 Oct. B4 and B6 plans finalised 2 Oct: B4 follows its start dates and colours by size; B6 replaces the 30 Sep plan. Erik's 2 Oct points built in | Plans final
Process deliverables Shayan T · one-off · P0 | Campaign-type list Wednesday, ad-type framework Friday, stabilisation proposal by end of week. Re-set on the 30 Sep call: ranking plan first, the rest by end of week | Ranking plan sent 1 Oct as agreed. Campaign-type list, ad-type plan (Bamboo first), frameworks and stabilisation proposal due end of week, 3–4 Oct. SB, SBV and SD held for creative, so the 1 Oct API launch did not happen | Due end of week
CooLinens Pillowcase launch Shayan T · one-off · P0 | PPC launch strategy delivered Monday 28 Sep, campaigns live with the listing | Launch workbook shared 28 Sep, revised with a strategy doc on Erik's feedback 29 Sep. Listing goes live on Amazon today, 2 Oct, and PPC launches with it | Launching today
Cadence & daily oversight All owners · daily · P1 | Daily spend check on the top 20% of campaigns, Tuesday to Friday | Daily huddles ran. No spend-check or change-log records posted. Monday meeting dropped; two Joseph calls cancelled | 0 of 4 logged
Source: #ppc-internal-channel, #ppc-managers-only, #amazon-ppc (Keyword Story thread), #ppc-leadership and the 30 Sep call with Erik and Joseph, 28 Sep to 2 Oct, read against the PPC Weekly Plan v5 of 28 Sep · pulled 2026-10-02

## Slide 3
PPC · BAMBOO · B4 AND B6 RANKING PLANS
Bamboo ranking push: done and next
02
PPC · Sep 28–Oct 2
B4 Bamboo Sheets, 4 Piece
29
exact keywords
$1,200
budget a day
$59.8K
nine weeks to 3 Dec
−$1,975
ad result, ads only
Starts by size as in the plan of attack: Queen and general 2 Oct, Full about 9 Oct, King about 13 Oct; head terms from the 16 Oct deal (Queen head 27 Oct)
Ads 16–25% of sales; about $440 a day of organic profit at goal repays the ad loss in about 4 days
B6 Bamboo Sheets, 6 Piece
23
exact keywords
$830
budget a day
$50.3K
nine weeks to 3 Dec
+$3,011
ad result, ads only
Batch 1 (King and Queen compounds) 1 Oct; Batch 2 18 Oct if Batch 1 holds; Queen head when Queen White is receiving (30 Oct cautious, 9 Oct if early)
Ads 12–17% of sales, under B6's 25% ceiling; replaces the 30 Sep B6 plan
KEY DATES
6–7 Oct
Prime Big Deal Days: budgets 1.5×, bids hold, not read
10 · 11 Oct
Day-7 reads: B6, then B4
14 Oct
First 60-click trial reads
18 Oct
B6 Batch 2 starts if Batch 1 holds
19 Nov
Black Friday week: budgets 2×
Rank with exact keywords only; reads count clean days, so deal days never flatter a keyword. Plans: Bamboo_Ranking_Plan_B4.docx and _B6.docx, with the Docs and explainer pages.

## Slide 4
PPC · WEEK OF SEPTEMBER 28 TO OCTOBER 2
Blockers and help needed
03
PPC · Sep 28–Oct 2
BLOCKER | WHAT IT IS COSTING | WHO MUST ACT | RECOMMENDATION | DECISION BY
Prime Big Deal Days is four days out with no PPC plan outside Bamboo | No deal-day budget or bid stance; the S4 deal shows 10 issues. Bamboo plans set theirs: budgets 1.5×, bids hold | Shayan T, Joseph | Set the deal-day budget today and clear the S4 deal issues | Today, Oct 2
Amazon set its own budget rules on about 20% of campaigns | Bids rise 50% over the event on campaigns we did not pick | All line owners | Sweep every Dynamic Up-and-Down campaign and strip the rules | Today, Oct 2
Bamboo push needs sign-offs before its first reads | B4 runs at 22–25% of sales 30 Oct–19 Nov if heads stay on; reads run against goals the system does not hold | Erik, Joseph, Operations | Erik: spend above 20%, heads between deals, cooling timing. Joseph: goals in Target Setting. Ops: Queen and Full White dates | Mon, Oct 5
Bamboo ownership is unresolved between Rana and Taquie | The member plan names Rana; Joseph asked for Taquie on 28 Sep | Erik with Joseph | Settle it Monday and reissue the member plan against it | Mon, Oct 5
Engine sign-offs and Q1 to Q8 are still open with Joseph | Section 7 rules and the new thresholds cannot be applied | Joseph, Erik | Walk the register in one sitting and sign off each item | Mon, Oct 5
THE 15 OPEN ITEMS CARRIED INTO NEXT WEEK
Campaign-type list + screenshot
Ad-type framework document
Stabilisation proposal
Creative for 14 held campaigns
Conquest PAT test staging
20 negative-keyword changes
BAMBOO-KING-WHITE dark campaign
Q1 to Q8 engine decisions
Section 7 rules sign-off
Prime Day deal-day budget
S4 deal issues (10)
Amazon budget-rule sweep
Canada Bamboo audits
Bamboo push sign-offs (Erik)
Bamboo rank goals in Target Setting
First cross-functional blocker this week: the held SB, SBV and SD campaigns need creative from Design before they can go live. Shipment Tracker rows USA237, 238, 241 and 251 sit with IP — Forecasting.

## Slide 5
PPC · WEEK OF OCTOBER 5 TO 9
Next week
04
PPC · Oct 5–9
WORKSTREAM | WHAT WE WILL DO | BY WHEN | PRIORITY | CARRYOVER
Prime Big Deal Days Shayan T | Run the Oct 6–7 event: deal-day budgets live, Amazon's own budget rules stripped, S4 deal issues cleared | Mon, Oct 5 | P0 | N — new
Bamboo ranking push Shayan T with Joseph | Get the sign-offs, write the rank goals to Target Setting and go live; day-7 reads 10 Oct (B6) and 11 Oct (B4), first 60-click trial reads 14 Oct | Mon, Oct 5 · reads 10–14 Oct | P0 | N — new
CooLinens Pillowcase Shayan T | First live week: daily spend, search-term and conversion checks, PAT additions from Shayan R, launch read at the Friday close | Daily · read Fri, Oct 9 | P0 | N — new
Audit cycle All three | Run the next cycle on all nine, Bamboo Monday and the rest Tuesday. This cycle closes today with the last three feedbacks | Mon, Oct 5 | P0 | N — new cycle
Engine register Zarlish | Move the register to changed-findings-only and get Section 7, Q1 and Q3 signed off | Mon, Oct 5 | P0 | Y — since Oct 2
Other campaign types Shayan T | Send the campaign-type list, the ad-type plan for Bamboo and the frameworks for the other products (agreed on the 30 Sep call), brief creative for the held SB, SBV and SD campaigns, then launch them through the API | End of week, Oct 3–4 · launch TBC Mon | P0 | Y — since Sep 30
Stabilisation proposal Shayan T | Deliver catalog prioritisation, team structure, the finalised cadence and the development list, with priorities and due dates as Erik asked on 30 Sep | End of week, Oct 3–4 | P0 | Y — since Oct 2
Oversight & onboarding All owners | Log the daily spend checks, and run Ivan's first full week with EOD outputs | Mon, Oct 5 | P1 | Y — since Sep 29
P0 fails the cycle if it slips. · Dates marked TBC are set at Monday's alignment, not assumed here. · Bamboo plan start dates of 1–2 Oct move to the sign-off date; reads move with them.

## Slide 6
PPC · DEPARTMENT OPERATING PLAN
Cadence
05
PPC · Sep 28–Oct 2
RHYTHM | WHAT RUNS | OWNER | WHEN | LOGGED IN
Daily Every owner | Spend check on the top 20% of each owner's campaigns, manual changes logged with expected results | Line owners | Tue–Fri | Change log
Daily Bamboo push | Spend, rank and stock check on every pushed keyword; reads on clean days only, deal days not read | Shayan T | Daily | Change log
Daily Team | Short check-in across the three members on what changed and what is blocked | All three | Daily | Huddle
Monday Cycle start | Audits through the app, full review by all three, Bamboo feedback shared and executed the same day | Shayan T | Monday | Managers channel
Tuesday–Wednesday Cycle | Consolidated feedback on the remaining products, executed by Joseph on Tuesday | All three | Tue–Wed | App + register
Thursday Tuning | Tuning run on Monday's changes, reviewed by all three, executed by Joseph. Bamboo margin reset | Joseph | Thursday | App
Friday Close | Read of where each product stands, manual adjustments, this deck, oversight feedback to Joseph | Zarlish | Friday | This deck
Run in full for the first time this week. · The Monday meeting was dropped and two Joseph calls were cancelled; Tuesday and Friday are the standing slots.

## Slide 7
PPC · DEPARTMENT OPERATING PLAN
Owner directions
06
PPC · Sep 28–Oct 2
OWNER | DIRECTION FOR THIS CYCLE | CADENCE | REPORTS TO | ESCALATES TO
Shayan Taquie Dept lead · Cooling · 2 lines | Own the cycle and Joseph coordination, the campaign-type list, the ad-type framework, the proposal, Prime Day and the B4/B6 ranking push | Daily + Mon + Fri | Erik & Joseph | Erik
Shayan Rana Bamboo · 3 lines | Bamboo daily work and the Canada deals, app-side feedback Friday. Bamboo ownership is under review | Daily + per cycle | Shayan T | Joseph
Zarlish Satin · 4 lines | Satin daily work, the consolidated engine register and the Friday read. Register goes changed-only | Daily + Friday | Shayan T | Joseph
Joseph Audit engine · outside PPC | Run the nine audits, execute agreed changes through the app, sign off Section 7, Q1 and Q3, and write the Bamboo rank goals to Target Setting | Per cycle | Erik | Erik
Ivan Onboarding · from 2 Oct | Foundation on catalog, products and process. EOD output daily: done, next, blockers, questions | Daily EOD | Shayan T | Shayan T
Whole department Standard for every audit | All three review every audit in full. Nothing executes that a reviewer has not signed off | Per cycle | Shayan T | Erik
Line counts are the daily-manual-work owners in the PPC Weekly Plan v5 of 28 Sep. · Bamboo ownership is open with Joseph and Erik.