ECOTERO LLC · AMAZON US · COOLINENS

CooLinens Cooling Pillowcases 2-Piece

PPC Launch Strategy and Plan, v1.2

The strategic reasoning, expected costs, ranking requirements and launch tracking behind the launch workbook, benchmarked on our own Sleephoria cooling-pillowcase launch. Prepared 29 September 2026 for brand-owner review. Version 1.2 takes in the USA competitor and PPC analysis of 28 September and closes every item in the review of 29 September.

| Field | Value |
| --- | --- |
| Product | CooLinens Cooling Pillowcases 2-Piece (BreezeWeave knit, hidden zipper): 12 children, Standard, Queen and King in White, Blue, Dark Grey and Light Grey. The parent ASIN is assigned when the variation merge now under way completes; the command center currently records B0H5X3L7M3 as the parent, which is the Blue King child. |
| Go-live | Wednesday 30 September 2026 (PPC go-live and first price step), following the launch channel of 29 September. Every date in this plan moves with the go-live date cell in the workbook. |
| Objective declaration | Growth/Scale, confirmed 29 Sep 2026. The ranking allowance is available; the launch-phase conditions below decide when it is spent. |
| Companion files | COOLINENS_Cooling_Pillowcases_2PC_Launch_Workbook_v1.2.xlsx (every figure here traces to its Cross-check tab); the draft launch workbook of 29 Sep 2026 (original tabs kept inside it); USA competitor and PPC analysis with its evidence workbook (28 Sep); review and corrections register (29 Sep) |
| Measurement windows | CooLinens: SellerBoard 1 to 28 Sep 2026. Sleephoria: monthly P&L Oct 2025 to Sep 2026; PPC by keyword 1 Oct 2025 to 21 Sep 2026; rank radar 1 Jul to 28 Sep 2026. Market: DataDive niche and live US search panel, 28 Sep 2026; SQP 4 weeks to 23 Aug 2026; Data Rova last 4 weeks (draft MKL). |
| Economics basis | COGS by Price Stage sheet (10 Sep 2026): landed COGS King $4.70, Queen $4.06, Standard $3.86 incl. $0.90 rebased freight; FBA per SKU; referral 15%. COGS is not yet confirmed and not loaded in SellerBoard, so every ceiling is provisional until it is. |
| Governing documents | PPC SOPs in the PPC-Audit repository (Launch Stage, Ranking Push, Exact Campaign, Placement and Modifier, Sibling Arbitration, Auto, PAT and Conquest, Harvest, Margin Table, Prediction Scoring); thresholds file; Price Increase and Buy Box Safety Standard (10 Sep); launch brief (10 Sep); rulings of 29 Sep on placement, sales-target basis, conversion sensitivity, review gate and go-live (section 9.6). |

# The plan in five lines

- CooLinens goes live on 30 September into the off-season, with 125 reviews reported but only 9 showing on the listing, into crowded auctions (REST, Bambaw and Beckham advertise on 24 to 26 of 30 searches), at a live price ($15.99 Queen) that earns $4.31 a unit.

- Our own Sleephoria cooling pillowcase did exactly this in October 2025: $12,273 of ads in three months, a net loss of $10,084, demand down 58% by February in sessions, then a summer stock-out that took its best ranks from 6 to 47.

- So Phase 1 (30 September to late January) buys evidence, reviews and price, not rank: ten 100-click exact tests, one per buyer intent, a probe on the head term we share with Sleephoria, and a branded campaign, for $103 a day against $1,635 in the draft.

- The price climbs every 14 days, never more than 13% above its own trailing 60-day average, from $15.99 to a $21.99 Queen holding price on 9 December, which lifts what a click can afford from $0.94 to $1.48.

- The ranking push is priced now, not promised: $538 a day if every 500-plus term ran at its daily sales target, $295 on Amazon's measured purchase level. Which terms it funds is decided on 11 January from what the tests actually show, and it is released into the rising season (target 1 February) once stock and head-term ownership are settled.

## The position

| Figure | Value | Basis |
| --- | --- | --- |
| Live price (mistaken Vine price since 14 Sep) | $14.99 Std, $15.99 Queen, $16.99 King | SellerBoard, 1 to 28 Sep 2026 |
| Contribution per unit at live price | $3.12 to $4.98 across the 12 children (Queen $4.31) | Price less 15% referral, FBA and landed COGS |
| Units sold 1 to 28 Sep | 93 (about 39 free Vine units, about 54 paid) | SellerBoard |
| Reviews | 125 reported (Vine, 23 Sep); 9 showing on the Queen listing at 4.8 stars (28 Sep) | Launch channel; competitor analysis |
| Stock | 2,981 fulfillable units; 0 in production; 0 inbound | 28 Sep (competitor analysis); SellerBoard per child |
| Draft workbook | 73 keywords in 41 exact campaigns, +100% top of search on a full base bid, $1,635/day, 87 sales/day | Draft launch workbook, 29 Sep |
| Draft workbook stock runway | 34 days (to about 2 Nov) | 2,981 divided by (86.8 + 2 organic) |
| Paid competition | REST, Bambaw, Beckham on 24 to 26 of 30 searches; 5 brands advertise on our product page | Live search panel, 28 Sep |
| Sleephoria launch, first 3 months | $12,273 ad spend, net loss $10,084 | SellerBoard, Oct to Dec 2025 |

What this table decides

- The product is not ready to buy rank in October on price, season or stock, and it has no conversion evidence of its own yet.

- The draft workbook would spend its stock in five weeks and repeat Sleephoria's fourth-quarter loss at seven times the daily rate.

- What can be done now is cheap and fast: collect a 100-click conversion read on every intent, raise the price, bank reviews, settle the head term with Sleephoria, and place the reorder.

## Findings

| # | Finding | Where |
| --- | --- | --- |
| 1 | The draft prices every click against $1.63 to $4.39 of contribution taken from the old COGS sheet at the mistaken live price. On the rebased COGS and the go-live price it is $4.94 to $6.68, and $7.91 to $10.93 at the holding price. The $0.38 break-even click quoted for the head term is really $0.94 at go-live and $1.48 at $21.99. | 2B.1 |
| 2 | The draft build conflicts with the launch SOPs: bids seeded from doubled suggested bids (a bid is never invented at creation), 73 keywords in 41 campaigns at once (batches are 8 to 12), no effective search-volume floor (terms down to 51 searches a month; ranking needs 500+), a +100% top-of-search modifier on a full base bid, and competitor targeting at launch with $0.45 bids (below the $0.50 floor; conquest opens later). | 2A, 4.5, 6 |
| 3 | Sleephoria is the right benchmark and it disagrees with the draft: on its non-branded launch terms it paid $1.75 a click and converted 15.6%; on the head term $1.74 and 15.7%. Its launch month ran at $226 a day and about 21 ad orders a day, not 87. The draft's conversion column is click share times 1.5, not a measured rate. | 2.1, 4.2 |
| 4 | The head-term sales target the draft carried (13.7 a day) still contains that 1.5 uplift. On the brand owner's 15 September basis it is 12 a day ($211 a day); on Amazon's measured purchases it is 5 a day ($88). The two market levels differ 2.6 times, so the push budget is a range until the probe reads. | 4.2 |
| 5 | Review count: on all 51 tracked terms the top-5 competitors hold a median 673 to 3,852 reviews; CooLinens has 125 reported and 9 showing. SOP-23 reads under half the median as far behind. Ruling C4 keeps that as a risk note per term and decides the push on observed results. | 3.2, 4.4 |
| 6 | Season and stock: Sleephoria's sessions fell 58% from October to February and recovered in June. With no reorder and a lead time like Sleephoria's (about 200 days), stock reads green only below 13.5 units a day. | 3.3, 1.4 |
| 7 | "cooling pillow cases" (30,202 searches) is shared with Sleephoria. The ownership composite ranges from 92% CooLinens down to 43%, depending on which stock pace is read; the probe decides. | 4.7 |
| 8 | The auctions are crowded: REST, Bambaw and Beckham appear as sponsored results on 24 to 26 of 30 live searches and REST runs brand banners on 20. Our own brand search already shows REST and Beckham ads, and five brands advertise on our product page. | 6.2 |
| 9 | Of 16 competitor targets, five pass the entry test at the holding price on price and the 4.8 rating (HOMFINE, Elegear silver, REST, Beckham, Bambaw) and one (the second REST listing) is held for a size check. Conquest opens at Phase 3. | 6.3 |
| 10 | Nothing is set up to track the launch: product 70 has no price, fee or cost in the command center, SellerBoard carries $0 product cost for CooLinens, and there is no rank tracker for CooLinens in DataDive. | 7 |

## Action plan at a glance

| When | Action | Owner (role) | Money | Success measure | Ref |
| --- | --- | --- | --- | --- | --- |
| Before go-live | Confirm COGS for both pillowcase brands; load into SellerBoard and the command center (product 70 price, fees, cost) | Finance / Data | None | Product 70 shows break-even ACoS | 9.2 |
| Before go-live | Create a DataDive rank tracker on all 73 launch terms; switch on weekly SQP; confirm the parent ASIN after the merge | PPC | None | Daily ranks from day 1 | 7 |
| Before go-live | Reconcile the 9 reviews showing with the 125 reported; confirm Light Grey Standard stock (derived at 81 units) | Brand Management / Supply Chain | None | Counts match | 6.3, 1.4 |
| Before go-live | Final images; off-Amazon prices at or above the first Amazon step; place the reorder decision | Brand Management / Supply Chain | PO | Confirmed arrival date | 1.4 |
| 30 Sep | First price step (Q $17.99, K $18.99, S $16.49); ten tests live at half base bid and 100% top-of-search modifier; branded exact | PPC / Brand Management | $103/day | Featured Offer held; tests on pace | 2A.2 |
| 7 Oct | Day-7 read: delivery, expected CPC against realised, placement split, Buy Box | PPC | None | Every test on pace; top of search carries most clicks | 7.1 |
| 14 Oct | Second price step; head probe at 100 clicks; any test with 0 orders at 50 clicks stops | PPC | Released budget returns to reserve | Probe verdict or extension to 200 | 4.7 |
| 14 to 28 Oct | Head-term ownership declared from the probe | PPC Lead | None | Declaration filed; other brand walls the term | 4.7 |
| 28 Oct | Third price step; tests reach 100 clicks; Phase-2 entry: phrase and broad per intent, Auto close-match, tail exacts, self-targeting | PPC | Set at entry (about $150 to $200/day) | Data completeness at least 85%; COGS confirmed | 5 |
| 9 Dec | Holding price reached for Queen ($21.99) and Standard ($19.99); King $23.99 on 23 Dec | Brand Management | None | Session conversion at least 12% | 2B.2 |
| Mid Dec | Phase-3 check: competitor targeting on the five passing targets | PPC | 100-click cap per target | Entry test still passes; stock green | 6.3 |
| 11 Jan | Push release list from observed results against the conditions in 4.4 | PPC Lead / Brand owner | None | Terms named with their budgets | 4.4 |
| 1 Feb (target) | Sized ranking push released into the rising season | PPC | Ceiling $538/day | Rank stable 2 weeks at target before taper | 4.3 |

## What it costs

| Phase | Window | Spend | Expected | Against |
| --- | --- | --- | --- | --- |
| Phase 1: evidence and price | 30 Sep to 27 Oct (4 weeks) | $103/day, about $2,880 ($108/day with Decision 7) | About 39 clicks and 6 ad orders a day; a 100-click read on each of 10 intents; net after ads about minus $44/day (minus $311/week), narrowing with each price step | Draft: $1,635/day. Sleephoria launch month: $226/day |
| Phase 2: discovery and tail | 28 Oct to late Jan | Set at Phase-2 entry; indicative $150 to $200/day | Harvest of converting search terms; profit terms at max profitable CPC | Launch mix target: ranking 50, discovery 30, conversion 15, defensive 5 |
| Ranking push | From 1 Feb | Release list from observed results; ceiling $538/day ($295 on the SQP basis, $349 at 24% conversion) | 36 units/day at the full ceiling; 83 days of stock without a reorder | Requires the reorder and the conditions in 4.4 |

What this table decides

- Only one phase commits money now, and it is the cheapest: $103 a day, below Sleephoria's launch rate and 6% of the draft.

- The push is priced, not promised: $538 a day is the ceiling if every 500-plus term ran at once; the terms actually funded are named on 11 January from their own test results.

Decisions that need someone outside PPC - Brand owner: approve Option A (Phase-1 envelope $103/day), or B, C or the competitor analysis's mixed test D, with the costs in 2A.1. - Brand owner: the ACoS rule for ranking spend (2A.1) and acknowledgement that launch TACoS will run above the 15% to 25% reference band until the push ends. - Supply Chain with the brand owner: the reorder quantity and PO date. - PPC Lead: own-ASIN self-targeting from go-live as a defensive exception (Decision 7) and the first competitor-targeting pool for Phase 3 (Decision 8). - PPC Lead, reviewed by Brand Management: head-term ownership between CooLinens and Sleephoria after the probe. - Brand Management: the price ladder and holding price, including off-Amazon price floors. - Finance / Data: confirmed COGS before go-live.

# 1 Product story

## 1.1 History

CooLinens is the accessible-premium sibling of our Sleephoria cooling pillowcase: the same BreezeWeave knit and hidden zipper, positioned one price tier higher. The dated events that shape the launch:

- 10 Sep: Channel opened. Break-even Vine pricing proposed ($14.99 to $16.99). The brand owner asks for a higher launch margin to avoid Buy Box trouble when raising later; the launch brief sets a Vine price of $19.99 to $24.99 stepping to $27.99 to $33.99.

- 11 to 12 Sep: Buy Box safety standard issued (moves governed by the gap to the 60-day average). Vine cut from 400 to 350 enrollments and started.

- 14 Sep: Vine went live at the old break-even prices by mistake. The brand owner ruled not to rush the price up. Every paid sale since has anchored the reference price at $14.99 to $16.99.

- 16 to 28 Sep: COGS not in SellerBoard again; question raised whether COGS covers the full 2-pack plus packaging for both pillowcase brands.

- 23 to 24 Sep: 125 Vine reviews reported. $27 of spend traced to a stray campaign, paused 25 Sep. 24 TikTok creators approved for samples; DTC site about 2 weeks out.

- 28 Sep: USA competitor and PPC analysis: crowded paid auctions, 9 reviews showing on the listing, 2,981 fulfillable units, and three errors in the draft model (conversion from click share, a bid ceiling used as CPC, conflicting grouped budgets).

- 29 Sep: Draft launch workbook delivered; the brand owner asks for the strategy, Sleephoria benchmark, competitor research, expected CPCs, sales and clicks per day to rank, and launch tracking. Version 1.1 of this plan is reviewed (7 must-fix items, 5 rulings, all closed here). The launch channel moves go-live to 29 or 30 September.

## 1.2 Current situation, on today's data

| Child | Stock | Paid units 1 to 28 Sep | Sessions | Price | Note |
| --- | --- | --- | --- | --- | --- |
| Dark Grey Queen | 408 | 8 | 40 | $15.99 | Routed SKU for core and Queen terms; highest stock |
| Light Grey Queen | 275 | 11 | 45 | $15.99 | Best paid Queen seller |
| Blue Queen | 277 | 0 (9 Vine) | 26 | $15.99 |  |
| White Queen | 284 | 0 | 1 | $15.99 |  |
| White King | 272 | 0 | 4 | $16.99 | Routed SKU for King terms; best King contribution |
| Dark Grey King | 176 | 14 (2 via ads) | 50 | $16.99 | Best paid seller overall; lowest King stock |
| Blue King | 240 | 3 (30 Vine) | 76 | $16.99 | Most sessions, almost all Vine |
| Light Grey King | 238 | 3 | 20 | $16.99 |  |
| White Standard | 286 | 4 | 14 | $14.99 | Routed SKU for Standard terms |
| Blue Standard | 285 | 7 | 39 | $14.99 |  |
| Dark Grey Standard | 159 | 4 | 27 | $14.99 | Weakest economics ($5.76 FBA) |
| Light Grey Standard | 287 (DOH matrix) | 0 | , | $14.99 | Missing from SellerBoard export |

Source: SellerBoard Ecotero account, CL-CLG-PC SKUs, 1 to 28 Sep 2026. Paid units exclude units carrying a promotion value (Vine).

What this table decides

- The apparent "King is the best seller" reading is Vine: 30 of Blue King's 33 units were free. Paid demand is spread thin and evenly, no child has earned a routing change.

- Unit-session conversion reads 27% but is inflated by Vine and the low price; plan on 15 to 20% at the stepped prices.

## 1.3 Context-corrected metrics

| Correction | What it changes | Where it applies |
| --- | --- | --- |
| Economics on the go-live and holding prices with rebased COGS, not the old sheet at the live price | Contribution rises from $1.63 to $4.39 to $4.94 to $6.68 (go-live) and $7.91 to $10.93 (hold) | Every ceiling in sections 2B and 4 |
| Sleephoria conversion read on non-branded terms | Its 23% lifetime ad conversion includes branded search ("sleephoria" alone: 938 orders). Non-branded launch terms convert 15.6%; its launch month converted 24%, carried as a sensitivity | Planning conversion in 4.2 |
| The draft's conversion rate | It was click share times 1.5, a share of clicks, not orders per click | Every push size and ceiling in 4.2 |
| The draft's daily sales targets | They carried the same 1.5 uplift; re-derived on the brand owner's 15 Sep basis (Data Rova divided by 28, times click share, plus 20%, rounded up) with SQP measured purchases as the low case | Push sizing in 4.2 and 4.3 |
| Sleephoria CPC read in its launch window | Its CPC was $2.62 in Oct to Nov 2025 against $1.65 over twelve months: a 1.59 times launch premium | Expected CPC in 4.2 |
| Reviews shoppers see | 125 reported, 9 displayed on the Queen listing on 28 Sep | Competitor entry test (6.3); review risk (3.2) |
| A price move makes the next 7 days of conversion and ACoS provisional | Every step in the ladder opens a 7-day provisional window | 7.1 checkpoints |

## 1.4 Inventory, days of cover and SKU routing

Stock is the binding constraint on how hard this launch can push. Stock reads green only when cover exceeds the reorder lead time plus 21 days, sized against the whole plan, not the first tests alone. Yellow freezes push spend; red (under 21 days) re-points the campaign to the next child the same day.

| Reorder lead time | Max units/day that stays green | Phase-1 pace | Option B pace | Push ceiling pace | Draft workbook pace |
| --- | --- | --- | --- | --- | --- |
| 60 days | 36.8 | 9.9 | 31.9 | 36.0 | 88.8 |
| 90 days | 26.9 | 9.9 | 31.9 | 36.0 | 88.8 |
| 120 days | 21.1 | 9.9 | 31.9 | 36.0 | 88.8 |
| 150 days | 17.4 | 9.9 | 31.9 | 36.0 | 88.8 |
| 200 days (Sleephoria's) | 13.5 | 9.9 | 31.9 | 36.0 | 88.8 |

Source: Inventory Runway tab, 2,981 fulfillable units on 28 Sep, cover computed from the 28 Sep column. Units a day include organic at 2 a day plus 0.3 per ad order (a soft coefficient measured on 14 and 28 Oct).

What this table decides

- Phase 1 is the only pace that stays green without a reorder. A February push at full pressure needs the reorder placed now and landing before the push ends.

- Routing stays as drafted: Dark Grey Queen, White King, White Standard, each with the highest stock or best contribution in its size. When a routed child falls under 21 days it re-points in this order: Queen Dark Grey, Light Grey, Blue, White; King White, Blue, Light Grey, Dark Grey; Standard White, Blue, Light Grey, Dark Grey.

- Light Grey Standard is missing from the 28 Sep SellerBoard export; derived from the fulfillable total it holds 81 units and reads yellow. Confirm before go-live.

# 2 What our own launch produced, Sleephoria as the benchmark

Sleephoria Cooling Pillowcases (product 43) is the same fabric one tier lower. It launched Vine in July 2025 and PPC in October 2025, and it is the closest evidence we have for CooLinens' CPCs, conversion, sales needed to rank, and what goes wrong.

## 2.1 Parent-level performance

| Month | Units | Sales | Ad spend | TACoS | Sessions | Unit session % | Net profit |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Oct 2025 | 751 | $11,483 | $6,125 | 53% | 5,398 | 13.9% | minus $4,992 |
| Nov 2025 | 552 | $9,036 | $3,895 | 43% | 4,266 | 12.9% | minus $3,190 |
| Dec 2025 | 417 | $6,600 | $2,253 | 34% | 3,440 | 12.1% | minus $1,902 |
| Jan 2026 | 252 | $4,886 | $1,281 | 26% | 2,487 | 10.1% | minus $903 |
| Feb 2026 | 285 | $5,123 | $855 | 17% | 2,253 | 12.6% | minus $623 |
| Jun 2026 | 492 | $8,909 | $2,058 | 23% | 4,091 | 12.0% | minus $1,066 |
| Aug 2026 | 289 | $6,047 | $1,295 | 21% | 2,915 | 9.9% | +$276 |
| Sep 1 to 28 | 80 | $1,789 | $213 | 12% | 941 | 8.5% | +$369 |

Source: SellerBoard, Ecotero account, SL-CLG-PC SKUs. Full twelve months in the Sleephoria Benchmark tab.

What this table decides

- A Q4 cooling launch loses money while demand falls: minus $10,084 in three months, with sessions down 36% by December and 58% by February.

- What worked was price discipline: four +$2 steps took the price from about $15.50 to $22.50 while conversion held 9 to 15% and TACoS fell from about 55% to about 11%. That path is the basis for the CooLinens ladder.

## 2.2 Rank outcome

| Term | Searches | Avg rank Jul | Aug | Sep | Best | Sleephoria clicks | CPC | CVR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| cooling pillow cases | 30,202 | 52.5 | 33.2 | 53.7 | 5 | 1,186 | $1.74 | 15.7% |
| cooling pillow cases for hot sleepers | 2,630 | 35.5 | 40.3 | 33.5 | 13 | 16 | $0.47 | 12.5% |
| cool pillow cases | 2,269 | 38.7 | 41.4 | 48.1 | 23 | 155 | $1.56 | 18.7% |
| cooling pillowcase | 2,315 | 54.2 | 52.2 | 85.6 | 28 | 2 | $1.69 | , |
| cooling pillow cases king | 819 | 6.4 | 17.2 | 47.4 | 3 | , | , | , |
| cooling pillow cases with zipper | 921 | , | , | 38.6 | 10 | 199 | $1.29 | 10.1% |
| cooling pillow cases standard size | 545 | , | , | 20.8 | 9 | 266 | $2.06 | 15.4% |

Source: DataDive rank radar (Sleephoria, 98 terms), 1 Jul to 28 Sep 2026, in the Sleephoria Benchmark tab rank table; command-center PPC, 1 Oct 2025 to 21 Sep 2026.

What this table decides

- Sleephoria never held page one on the head term; its average sat at 33 to 54. Its real rank assets were mid-tail terms, King, zipper, Standard, hot sleepers, where it reached 3 to 13.

- Those assets collapsed when stock ran out (King term 6 to 47). Rank without stock cover is rented, not owned.

## 2.3 What made it work, and what did not

| Characteristic | Evidence | What CooLinens does with it |
| --- | --- | --- |
| Conversion survived price increases | 9 to 15% unit-session conversion from $15 to $22.50 | Ladder the price every 14 days to a $21.99 Queen holding price |
| Brand demand became the cheapest orders | "sleephoria" 938 orders at 14.8% ACoS; "sleephoria cooling sheets" 281 at 14.6% | Branded exact from day 1 to catch TikTok and DTC brand searches |
| Discovery lanes were most efficient | Last clean week: auto and product lanes 113 of 128 clicks and 25 of 28 orders | Open Auto close-match and broad at Phase 2, harvest at 3 orders |
| Mid-tail terms ranked, the head term did not | Best 3 to 13 on King, zipper, Standard, hot sleepers; head never better than 5 and averaging 33 to 54 | Test the mid-tail intents first; treat the head term as a probe until owned |
| Losses in the launch quarter | minus $10,084 Oct to Dec 2025 | Phase 1 at $103/day; push in the rising season |
| Stock-outs destroyed rank | 8 of 12 children low or out by Sep 2026; King rank 6 to 47 | Reorder now; projected cover checked before any push |
| Repeated process errors | Price set wrong, COGS missing, a main image with text got the listing suppressed | Pre-launch checklist in 8.3 |

## 2.4 Build status per segment and match type

CooLinens has nothing live. The draft built 73 keywords into 41 exact campaigns (21 single-keyword, 20 grouped) and one product-targeting set. This plan builds ten single-keyword exact tests and branded exact at go-live, one test per buyer intent, and the phrase, broad, auto, tail and self-targeting layers at Phase 2 (section 5).

## 2.5 Advertised-SKU register

| Segment | Routed child | Why |
| --- | --- | --- |
| Core, Hot Sleeper, Zipper, Queen | Dark Grey Queen | Highest stock of any child (408 to 417); Queen is 39% of the PO; Dark Grey Queen was Sleephoria's best seller (27% of its units) |
| King | White King | Joint-best King contribution ($4.76 FBA) and the highest King stock (251 to 272) |
| Standard | White Standard | Best Standard contribution ($5.22 FBA vs $5.76 for the greys) and 282 to 286 units |

# 2A Earning potential and the declarations

## 2A.1 Objective, the ACoS rule and the spend envelope

The declared goal is Growth/Scale, so the ranking allowance, spending above break-even to buy position, is available. The SOPs decide when it can be spent, and what they say about ACoS answers the open question in the launch brief:

- Break-even ACoS = contribution divided by price. For non-ranking spend, target ACoS is 50% of break-even and the maximum acceptable is 75%.

- Ranking campaigns run inside an absolute ACoS band of 50 to 80% while a sized push is live. There is no weeks-since-launch multiple in the SOPs; the 1.2 times (app setting) and 1.5 to 1.7 times (Slack, 6 Sep) figures in the brief both sit inside that band at CooLinens' holding prices.

- Every click is also tested as CPC divided by max profitable CPC: up to 0.8 safe, 0.8 to 1.0 at ceiling, 1.0 to 1.5 allowed only inside a sized push, above 1.5 unjustifiable outside one.

- A contribution under $6 a unit is "thin": expected CPC must then be at or under a third of the margin. The go-live step lifts Queen ($6.01) and King ($6.68) just out of thin; Standard ($4.94 at go-live, $5.79 on 14 Oct) stays thin until the 28 Oct step ($6.21).

- The launch TACoS reference band is 15 to 25%. A launch reads far above it by construction; that reading goes to the PPC Lead and needs the brand owner to approve a below-break-even run with an end date, it is not exempt automatically.

Recommended ACoS rule: no ranking push until the conditions in 4.4 are met; once one is sized, cap it at 1.5 times break-even ACoS at the price then live (Queen at $21.99: 42.8% times 1.5 = 64%), inside the 50% to 80% band, with a weekly loss ceiling written before money moves. Phase-1 tests are not judged on ACoS; they are judged on delivering their 100 clicks and on expected CPC against max profitable CPC.

| Option | Spend/day | What it buys | Stock runs out | Against the SOPs |
| --- | --- | --- | --- | --- |
| A: recommended | $103 ($108 with Decision 7) | Ten 100-click tests, head-term probe, branded exact; about 39 clicks and 6 ad orders a day | After the Feb push is sized (302 days at Phase-1 pace) | Compliant except the placement ruling (C1) |
| B: October push | $369 | The ten tests at their full daily sales target; about 23 ad orders a day; about minus $1,249/week | About 1 Jan 2027 | Needs override: season, stock, sibling declaration |
| C: draft workbook | $1,635 | 73 keywords at +100% top of search; 87 sales/day target | About 2 Nov 2026 | Not compliant (finding 2) |
| D: competitor analysis's mixed test | $120 for 7 days ($840 cap) | 40% exact long-tail, 20% head-term test, 25% competitor targeting, 10% discovery, 5% brand | Not a stock question | Needs override: competitor targeting and discovery inside Phase 1 |

Option D is the competitor analysis's proposal, and it agrees with A on the essentials: a capped test of about $100 to $120 a day, bids bounded by economics, one tightly defined head-term test with its loss recorded apart from the profit lanes, and no promise of rank. It differs on what runs in the first weeks. The launch SOP builds exact campaigns only in Phase 1 and treats competitor targeting as a Phase 3 surface, because a product with 9 visible reviews has not yet earned the comparison it would be conquesting on. A keeps the exact tests and carries D's two useful additions where the SOPs allow: own-ASIN self-targeting as a defensive exception (Decision 7), and the five competitor targets that pass the entry test prepared for Phase 3 (Decision 8).

## 2A.2 What is committed, and at what price

Only the ten tests and the branded campaign commit money at go-live. Each test is a single-keyword exact campaign on the routed child with a fixed bid: the base bid is half the expected cost per click and the top-of-search modifier is 100%, so the effective top-of-search bid equals the expected cost per click and other placements cost half (ruling C1). Each test is capped at 100 clicks over 28 days and stops early at 0 orders after 50 clicks. The head-term probe reads at 100 clicks on day 14 and runs on to 200 if it lands between 10% and 15.7%. Every campaign has at least a $5 daily budget; the click cap, not the budget, limits spend.

| Keyword | Intent | Searches | Expected CPC | Base bid | Source | Clicks/day | Budget $/day | Stops when |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| cooling pillow cases | Core | 30,202 | $2.76 | $1.38 | Sleephoria | 7.1 | $19.71 | 100 clicks (200 if extended) |
| cooling pillow cases for hot sleepers | Hot Sleeper | 2,630 | $0.75 | $0.38 | Sleephoria | 3.6 | $5.00 | 100 clicks, or 0 orders at 50 |
| cool pillow cases | Core | 2,269 | $2.48 | $1.24 | Sleephoria | 3.6 | $8.86 | 100 clicks, or 0 orders at 50 |
| cold pillow case | Core | 1,109 | $3.74 | $1.87 | Amazon median | 3.6 | $13.36 | 100 clicks, or 0 orders at 50 |
| cooling pillow cases with zipper | Zipper | 921 | $2.05 | $1.02 | Sleephoria | 3.6 | $7.32 | 100 clicks, or 0 orders at 50 |
| cooling pillow cases king | King | 819 | $1.28 | $0.64 | Amazon median | 3.6 | $5.00 | 100 clicks, or 0 orders at 50 |
| cooling queen pillowcases set of 2 | Queen | 819 | $2.64 | $1.32 | Amazon median | 3.6 | $9.43 | 100 clicks, or 0 orders at 50 |
| cooling pillow covers with zipper | Zipper | 639 | $3.50 | $1.75 | Amazon median | 3.6 | $12.50 | 100 clicks, or 0 orders at 50 |
| cooling pillow cases standard size | Standard | 545 | $3.27 | $1.64 | Sleephoria | 3.6 | $11.68 | 100 clicks, or 0 orders at 50 |
| cooling pillowcases standard set of 2 | Standard | 433 | $1.31 | $0.66 | Amazon median | 3.6 | $5.00 | 100 clicks, or 0 orders at 50 |
| Branded exact (coolinens terms) | Brand | None | $0.50 | $0.50 | Floor | None | $5.00 | Runs |
| TOTAL |  |  |  |  |  | 39.3 | $102.86 |  |

## 2A.3 Search terms, negation and harvest

Negatives are loaded when each campaign is built, not after spend: the tests carry negative-exact walls against each other; Phase-2 broad and auto carry negative-exact on every live exact term; wrong-intent roots from the MKL disqualifier list (silk, satin, body pillow, bamboo, "pillows" as a product) and four-pack intent ("set of 4") go in as negative phrase, never a blanket negative on "pillow" or "cooling pillow", which would block the core terms. Protector intent (Serta) stays in its own test, not in core. Word-order variants of a tested intent run in that intent's Phase-2 phrase and broad campaigns and get their own exact at 3 orders. A discovery search term reaching 3 orders graduates to its own exact campaign the same day and is walled in its source. Waste limits: 10% on exact, 40% on discovery.

# 2B Unit economics

## 2B.1 Per routed child and per price point

| Routed child | Price point | Price | Contribution | Break-even ACoS | Max CPC at 15.7% CVR | Margin class |
| --- | --- | --- | --- | --- | --- | --- |
| Dark Grey Queen | Live | $15.99 | $4.31 | 27.0% | $0.68 | Thin |
|  | Go-live | $17.99 | $6.01 | 33.4% | $0.94 | Standard |
|  | Hold | $21.99 | $9.41 | 42.8% | $1.48 | Standard |
|  | Premium target | $29.99 | $16.21 | 54.1% | $2.54 | Rich |
| White King | Live | $16.99 | $4.98 | 29.3% | $0.78 | Thin |
|  | Go-live | $18.99 | $6.68 | 35.2% | $1.05 | Standard |
|  | Hold | $23.99 | $10.93 | 45.6% | $1.71 | Standard |
|  | Premium target | $33.99 | $19.43 | 57.2% | $3.05 | Rich |
| White Standard | Live | $14.99 | $3.66 | 24.4% | $0.57 | Thin |
|  | Go-live | $16.49 | $4.94 | 29.9% | $0.77 | Thin |
|  | Hold | $19.99 | $7.91 | 39.6% | $1.24 | Standard |
|  | Premium target | $27.99 | $14.71 | 52.6% | $2.31 | Standard |

Source: Economics tab (all 12 SKUs). Contribution = price minus 15% referral minus FBA minus landed COGS. COGS unconfirmed; a higher confirmed COGS lowers every figure one-for-one.

What this table decides

- The price is the biggest lever in this launch: moving Queen from $17.99 to $21.99 lifts the affordable click by 57%, more than any bid change could.

- At the $29.99 premium target a click can afford $2.54, roughly the auction price, which is why the ladder continues after rank is won.

## 2B.2 Price ladder and the ranking price

Each child moves every 14 days from go-live. Every step is tested against the trailing 60-day time-weighted average price on the Price Model tab (counting only days the listing had a price, from 14 September) and stays at most 13% above it: amber under the Buy Box standard, which allows up to 15% in launch. Paid orders on 5 of the last 7 days are required before each move. Before every move the pre-flight reads the actual 60-day average from Business Reports and halves any step that would sit more than 15% above it.

Tested this way, the ladder reaches the holding price on 9 December for Queen ($21.99) and Standard ($19.99) and on 23 December for King ($23.99): three to five weeks later than version 1.1 assumed, and still before the push window. It holds there while a ranking push is live, because above 1.25 times the head term's $17.74 median clicked price the listing reads "outpriced" for a push. The steps on 25 November and 9 December fall inside the Black Friday to Cyber Monday window and are held if a deal runs. Off-Amazon listings must sit at or above each new price before the move.

## 2B.3 Reconciliation with parallel decision systems

| Source | What it says | How this plan resolves it |
| --- | --- | --- |
| Launch brief (10 Sep) | Vine $19.99 to $24.99, then launch $27.99 to $33.99 by 19 Oct | The Vine price went live at $14.99 to $16.99; the ladder re-bases from there and reaches the brief's launch targets around March |
| Buy Box standard (10 Sep) | Govern moves on the gap to the 60-day average; at most 15% in launch | Every step at most 13% on a formula-based average; one step per 14 days; same-day rollback |
| Launch brief, ACoS | 1.2 times (app) against 1.5 to 1.7 times (Slack): pick one | 1.5 times break-even inside the SOP's 50% to 80% ranking band (2A.1) |
| Sleephoria PPC plan (10 Sep) | Open decision: which sibling owns "cooling pillow cases" | Probe first, declare between 14 and 28 Oct (4.7) |
| Draft launch workbook (29 Sep) | 73 keywords in 41 campaigns, $1,635/day, +100% top of search | Replaced; every change listed in the Change Review tab for reviewer marks |
| USA competitor and PPC analysis (28 Sep) | Draft conversion is click share times 1.5; its "CPC" is a bid ceiling; grouped budgets conflict. Proposes a $120/day mixed 7-day test | Conversion replaced with Sleephoria's measured rates; expected CPC from actual CPCs; one budget per campaign. The mixed test is Option D |
| Review of v1.1 (29 Sep) | 26 findings: 7 must fix, 5 rulings | All closed in this version; each listed by finding number in the Change Review tab, rulings in 9.6 |
| Sleephoria ad archive, 3 Feb to 4 Mar 2026 | CPC $1.13, conversion 23.8%, ACoS 17.9% | Off-season and includes branded search, so reference only |

# 3 Diagnosis: the keyword universe and the conditions

## 3.1 Keyword universe by segment

| Segment | Launch terms | Searches/month | Phase-1 tests | Phase-2 exact (500+) | Tail exact (250 to 499) | Discovery (under 250) | Excluded |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Core | 19 | 41,548 | 3 | 5 | 6 | 5 | 0 |
| Hot Sleeper | 4 | 3,786 | 1 | 1 | 0 | 2 | 0 |
| Zipper | 10 | 3,131 | 2 | 0 | 4 | 4 | 0 |
| King | 16 | 6,734 | 1 | 5 | 6 | 3 | 1 |
| Queen | 14 | 4,626 | 1 | 1 | 8 | 4 | 0 |
| Standard | 10 | 2,856 | 2 | 0 | 3 | 5 | 0 |

What this table decides

- All 73 terms are one root family ("cooling pillowcase") split into six segments; one four-pack query is excluded because the offer is two pieces.

- The ten tests cover every segment and every routed child: three Core, one Hot Sleeper, two Zipper (the product's clearest difference), one King, one Queen and two Standard (where the category transacts most).

- Word-order variants are not tested separately: five King and two Queen variants run in their intent's Phase-2 phrase and broad campaigns (ruling C5).

## 3.2 Review risk per term

SOP-23 reads a term as far behind when our reviews are under half the median of its top-5 competitors. Ruling C4 (29 September) keeps that reading as a risk note per term, not a gate: the push decision in 4.4 uses observed results. On DataDive's 28 September rank grid across the 20 tracked competitors (CooLinens at 125 reported reviews; the listing showed 9 on 28 September, so the real position is weaker than this table reads):

| Terms | Top-5 median reviews | Half the median | Risk |
| --- | --- | --- | --- |
| Head and most core terms (cooling pillow cases, cooling pillowcase, cool pillow cases, pillow case cooling) | 3,526 | 1,763 | High: expect a long push and a higher cost per rank step |
| Hot sleepers, cold pillow case, set-of-2, standard terms | 3,852 | 1,926 | High |
| cooling pillow cases with zipper; cooling king pillow cases; king pillow cases set of 2 cooling | 1,292 to 1,328 | 646 to 664 | Medium |
| Zipper cluster (zippered, zipper, covers with zipper) | 1,757 | 879 | Medium |
| ice cool pillow case | 673 | 337 | Low once Vine reaches about 300 |

Source: DataDive niche "Cooling PillowCases (Updated)", keyword rank grid, 28 Sep 2026. Only tracked competitors are counted.

## 3.3 Seasonality

Sleephoria's sessions fell from 5,398 in October to 2,253 in February and recovered to 4,091 in June; Amazon's query volume for "cooling pillow cases" ran at 83,000 in the four weeks to 23 August against a 30,202 monthly average. Ranking pushes are timed into a rising seasonal index and never after the peak; a falling index is a dated deferral, not a decline. The push window therefore opens when weekly market query volume on the top five terms rises two weeks running, expected late January to February, and should be complete before the June peak.

# 4 Per-keyword and per-campaign mathematics

## 4.1 Objective per campaign

| Campaign type | Objective | Bidding | Placement |
| --- | --- | --- | --- |
| Exact tests (ten) | Ranking candidate: evidence first | Fixed; base bid half the expected CPC | Top of search +100%; others 0% |
| Head-term probe | Ranking candidate: sibling probe | Fixed; base bid half the expected CPC | Top of search +100%; verdict on top-of-search clicks |
| Branded exact | Defensive | Fixed at $0.50 | 0% |
| Phase-2 exact (untested intents) and tail exacts | Profitable conversion | Down-only at max profitable CPC | 0% |
| Phrase and broad per intent, Auto close-match (Phase 2) | Discovery | Down-only, capped | 0% |
| Self-targeting (Decision 7 or Phase 2) | Defensive | $0.50, permanent | None |
| Competitor targeting (Phase 3) | Conquest | Down-only | None |

## 4.2 Per-keyword plan: expected CPC and the sales and clicks needed to rank

This is the table the brand owner asked for. "Expected CPC" is what we expect to pay: Sleephoria's actual CPC on the term times its 1.59 launch-month premium where it has at least 15 clicks, otherwise Amazon's median suggested bid. "Plan CVR" is Sleephoria's own conversion on the term where it has at least 100 clicks, otherwise its pooled non-branded 15.6%. "Ratio" is expected CPC divided by what a click can afford at the holding price, at plan conversion and at Sleephoria's 24% launch-month conversion. "Sales/day" is the daily sales target to rank on the brand owner's 15 September basis (Data Rova units in the last 4 weeks divided by 28, times the slot's click share, plus 20%, rounded up) and on Amazon's measured purchases (SQP). Push clicks and budget use the 15 September basis.

| Batch | Keyword | Searches | Expected CPC | Sleephoria CPC / CVR | Plan CVR | Ratio at hold | Ratio at 24% | Sales/day (15 Sep) | Sales/day (SQP) | Push clicks/day | Push $/day |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | cooling pillow cases | 30,202 | $2.76 | $1.74 / 15.7% (1186) | 15.7% | 1.87 | 1.22 | 12 | 5 | 76.5 | $211 |
| Test | cooling pillow cases for hot sleepers | 2,630 | $0.75 | $0.47 / 12.5% (16) | 15.6% | 0.51 | 0.33 | 2 | 1 | 12.8 | $10 |
| Test | cool pillow cases | 2,269 | $2.48 | $1.56 / 18.7% (155) | 18.7% | 1.41 | 1.10 | 2 | 1 | 10.7 | $27 |
| Test | cold pillow case | 1,109 | $3.74 | None | 15.6% | 2.54 | 1.66 | 1 | 1 | 6.4 | $24 |
| Test | cooling pillow cases with zipper | 921 | $2.05 | $1.29 / 10.1% (199) | 10.1% | 2.17 | 0.91 | 1 | 1 | 10.0 | $20 |
| Test | cooling pillow cases king | 819 | $1.28 | None | 15.6% | 0.75 | 0.49 | 1 | 1 | 6.4 | $8 |
| Test | cooling queen pillowcases set of 2 | 819 | $2.64 | None | 15.6% | 1.79 | 1.17 | 1 | n/a | 6.4 | $17 |
| Test | cooling pillow covers with zipper | 639 | $3.50 | None | 15.6% | 2.38 | 1.55 | 1 | n/a | 6.4 | $22 |
| Test | cooling pillow cases standard size | 545 | $3.27 | $2.06 / 15.4% (266) | 15.4% | 2.68 | 1.72 | 1 | 1 | 6.5 | $21 |
| Test | cooling pillowcases standard set of 2 | 433 | $1.31 | None | 15.6% | 1.06 | 0.69 | 1 | n/a | 6.4 | $8 |
| Ph 2 | cooling pillowcase | 2,315 | $2.89 | None | 15.6% | 1.96 | 1.28 | 1 | 1 | 6.4 | $19 |
| Ph 2 | cooling pillowcases for hot sleepers | 1,023 | $1.44 | None | 15.6% | 0.98 | 0.64 | 1 | 1 | 6.4 | $9 |
| Ph 2 | cooling pillow cover | 924 | $3.43 | None | 15.6% | 2.33 | 1.52 | 1 | 1 | 6.4 | $22 |
| Ph 2 | ice fabric cooling pillowcases | 690 | $1.13 | None | 15.6% | 0.77 | 0.50 | 1 | n/a | 6.4 | $7 |
| Ph 2 | pillow case cooling | 662 | $3.33 | $2.10 / 17.6% (91) | 15.6% | 2.26 | 1.47 | 1 | 1 | 6.4 | $21 |
| Ph 2 | king size cooling pillow case | 654 | $2.60 | None | 15.6% | 1.52 | 0.99 | 1 | 1 | 6.4 | $17 |
| Ph 2 | king size pillow cases cooling | 651 | $3.03 | None | 15.6% | 1.77 | 1.15 | 1 | n/a | 6.4 | $19 |
| Ph 2 | cooling king pillow cases | 639 | $1.79 | None | 15.6% | 1.05 | 0.68 | 1 | 1 | 6.4 | $11 |
| Ph 2 | cooling pillow cases set of 2 | 616 | $1.14 | None | 15.6% | 0.77 | 0.50 | 1 | n/a | 6.4 | $7 |
| Ph 2 | king cooling pillow cases | 578 | $2.48 | None | 15.6% | 1.45 | 0.95 | 1 | 1 | 6.4 | $16 |
| Ph 2 | queen cooling pillow cases set of 2 | 570 | $2.59 | None | 15.6% | 1.76 | 1.15 | 1 | n/a | 6.4 | $17 |
| Ph 2 | king pillow cases set of 2 cooling | 565 | $1.91 | None | 15.6% | 1.12 | 0.73 | 1 | n/a | 6.4 | $12 |

Source: Keyword Plan tab: all 73 terms with every input, formula and the reasoning per row. Ratio = expected CPC divided by (contribution at the holding price times conversion).

What this table decides

- The head term needs 12 sales a day on the 15 September basis: 77 clicks and $211 a day. On Amazon's measured purchases (55.6 a day across all sellers against Data Rova's 143) it needs 5 a day and $88. The draft's 13.7 carried the 1.5 click-share uplift and is replaced. Until the probe reads, the head-term push is a range of $88 to $211 a day, not a figure.

- At plan conversion, 28 of the 72 live terms cost more than 1.5 times what a click can afford at the holding price. At Sleephoria's 24% launch-month conversion only 6 do, and the head term moves into the push-only band (1.22). The bands are provisional until the first 100-click reads replace both rates, which is what the tests are for.

- Where Sleephoria has real history, its CPCs sit well below the draft's $3.60, which the competitor analysis confirms is a bid ceiling, not a cost per click. The crowded auctions in 6.2 are the main risk to the expected CPC; the 7 October read tests it.

## 4.3 How each budget is derived

- Test budget per term = the larger of $5 and (100 clicks divided by 28 days, times the expected CPC). The head-term probe = 100 clicks divided by 14 days, times the expected CPC, held for 28 days in case it extends to 200 clicks.

- Daily sales target = Data Rova units in the last 4 weeks divided by 28, times the slot's click share, plus 20%, rounded up, never below 1 (the brand owner's 15 September basis). The SQP basis replaces Data Rova with Amazon's measured purchases per day.

- Push budget per term = daily sales target divided by planning conversion, times the expected CPC.

- There is no Phase-1 batch 2: a test that passes keeps its budget, so the envelope does not have to fund a second batch, and the ten tests reach 100 clicks by 28 October, the Phase-2 entry date.

- A push is funded only as a whole per term: fewer terms at full pressure, never more terms at lower pressure.

## 4.4 Ranking readiness: what a push needs

| Condition | Today | Met when | Owner |
| --- | --- | --- | --- |
| Observed results on the term (ruling C4) | No reads yet | At 100 clicks: conversion at least plan and at least the SQP market rate; click-through at least market; rank moving during the test | PPC Lead |
| Seasonal index rising | Falling (Oct to Feb) | Two consecutive rising weeks in SQP market volume | PPC Lead |
| Stock green for the whole push | Green only below 13.5 units/day at a 200-day lead | Reorder arrival keeps cover above the push length plus 21 days | Supply Chain |
| Price index at most 1.25 times the median clicked price | $17.99 = 1.01 times | Hold at Q $21.99, K $23.99, S $19.99 during the push | Brand Management |
| Head term owned | Shared with Sleephoria, undeclared | Declaration filed after the probe | PPC Lead |
| Economics confirmed | COGS unconfirmed; SellerBoard cost $0 | COGS confirmed and loaded; data completeness at least 85% | Finance / Data |
| Push fully specified | None | Target rank, daily sales target, clicks, weekly budget, weekly loss ceiling, horizon and checkpoint dates, prediction, dated release | PPC |
| Review risk (note, not a condition) | 125 reported, 9 shown against medians of 673 to 3,852 | Recorded per term in the push specification | Brand Management |

SOP-23 treats a review count under half the top-5 median as a bar to a push. Ruling C4 replaces that bar with the observed test above, on the brand owner's position that a push decision is a repeatable test on measured results; SOP-23 family F4 is flagged for amendment so the two do not conflict.

## 4.5 Placement

SOP-22 starts every launch campaign at zero modifiers. The review of 29 September pointed out the cost of that here: a full base bid with no modifier buys mostly rest-of-search and product-page clicks, so the probe and the tests would read conversion on the wrong placement for a top-of-search push. Ruling C1 therefore sets the base bid at half the expected cost per click with a 100% top-of-search modifier: the full expected cost per click is paid only on top of search and other placements cost half. This matches the entry model accepted on the Cooling Fitted Sheet (17 August) and is logged as a deviation from SOP-22.

Conversion is read by placement from day 1, and every verdict on a test or the probe uses top-of-search clicks. If top of search carries under 30% of a term's clicks, the placement is fixed before any money is added. The Placement SOP records the account's placement feed as missing; it must be confirmed before go-live, or placement reads come from the Amazon placement report by hand.

## 4.6 Release sequence

| Date | Released | Condition |
| --- | --- | --- |
| 30 Sep | Ten exact tests, head-term probe, branded exact (and self-targeting if Decision 7 is approved) | COGS loaded, images final, off-Amazon prices set |
| 14 Oct | Head-term probe verdict, or extension to 200 clicks; tests with 0 orders at 50 clicks stop | Probe at 100 clicks |
| 28 Oct | Phase 2: phrase and broad per tested intent (covering the word-order variants), Auto close-match, Phase-2 exact on untested intents (cooling pillow cover, ice fabric cooling pillowcases), tail exacts per segment, self-targeting | Data completeness at least 85%; at least 3 tests with a 100-click read |
| Mid Dec | Phase 3: substitutes auto; competitor targeting on the five passing targets | Stock green; entry test still passes at the price then live |
| 11 Jan | Push release list named from observed results | Conditions in 4.4 |
| 1 Feb (target) | Sized ranking pushes, highest revenue per dollar first | All conditions in 4.4 |

## 4.7 Head-term ownership: CooLinens or Sleephoria

| Reading | Sleephoria depth | CooLinens margin and depth | CooLinens share |
| --- | --- | --- | --- |
| 1. Sleephoria at its Jul to Aug pace (9.6 a day); CooLinens at test pace and the hold price | 33 days | $9.41; 302 days | 92% |
| 2. Sleephoria at its September pace (2.9 a day, stock-constrained) | 110 days | $9.41; 302 days | 78% |
| 3. As 2, with CooLinens at push pace and the $19.49 mid-ladder Queen price | 110 days | $7.29; 83 days | 43% |

Source: Sibling Ownership tab. Composite = margin per order times conversion on the term (15.7% for both until the probe reads) times inventory depth. Sleephoria margin $7.19 per order at a $20.38 average price.

The composite frames the question; it does not answer it, because the depth reading moves the result from 92% to 43%. The probe decides. At 100 top-of-search clicks: at least 15.7% and ownership goes to CooLinens; under 10% and Sleephoria keeps the term while CooLinens defends at floor. Between 10% and 15.7%, the most likely outcome at 100 clicks (15.7 orders plus or minus about 3.6), the probe runs on to 200 clicks and the PPC Lead compares it with Sleephoria's own trailing 30-day top-of-search conversion on the term. Until ownership is declared, neither brand opens a push on the term; on declaration the other brand walls the term in its broad, phrase and auto campaigns the same day and defends its own variants at floor.

# 5 Coverage

| Layer | Terms | Opens | How it is judged |
| --- | --- | --- | --- |
| Exact tests | 10 (one per intent) | Go-live | 100 clicks each; conversion by placement |
| Phrase and broad per tested intent | Covers 10 word-order variants with 500+ searches | Phase 2 | Harvest to exact at 3 orders |
| Phase-2 exact, untested intents | 2 (cooling pillow cover, ice fabric cooling pillowcases) | Phase 2 | Cost per order at or under contribution |
| Tail exacts, one campaign per segment | 27 (250 to 499 searches) | Phase 2 | Cost per order at or under contribution |
| Broad and Auto close-match | 23 (under 250 searches) plus unknown terms | Phase 2 | Harvest at 3 orders; waste at most 40% |
| Branded exact | coolinens, coolinens pillowcase, coolinens cooling pillow cases | Go-live | Share of brand clicks held |
| Named declines | Silk, satin, body-pillow, bamboo-pillow, "pillows", four-pack and Spanish terms marked irrelevant in the MKL | None | Negative phrase at build; reopen only if the listing adds the item |

The MKL is dated 10 Sep and its relevancy was never human-stamped; it must be refreshed and stamped before Phase 2. Sponsored Brands and video open after the head term is owned and a brand store exists. The competitor analysis shows why they cannot wait long: REST runs brand banners on 20 of 30 searches, Cozy Bliss runs video on 9 with almost no Sponsored Products, and our own brand search already shows REST and Beckham ads. The 15 to 25 second video in 6.4 should be made now so it is ready.

# 6 Competitor position

Two sources are combined here: the DataDive niche read (28 Sep; estimated sales) and the USA competitor and PPC analysis (28 Sep; 30 live searches, 24 product pages checked to the exact child ASIN, price histories). Where they differ on price, the live product page wins.

## 6.1 The competitive set, priced and dated

| Brand | Segment | Size checked | Price | Rating | Reviews | Est. sales/mo | Sponsored on (of 30) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CooLinens (ours) | Technical nylon, hidden zipper | Queen | $15.99 | 4.8 | 9 shown (125 reported) | , | , |
| Avolare | Technical nylon, hidden zipper | Queen | $15.19 | 4.4 | 3,862 | 2,351 | 12 |
| Bedsure (technical) | Technical nylon | Queen | $13.99 | 4.5 | 672 | , | 17 (brand) |
| QUTOOL | Technical nylon | Queen | $16.99 | 4.4 | 751 | 815 | 3 |
| Rifens Home | Technical nylon, zipper | Standard | $18.98 | 4.6 | 1,187 | , | 0 (organic on 27) |
| CHOSHOME | Technical, zipper | Standard | $14.60 | 4.4 | 1,759 | 1,484 | 0 |
| HOMFINE | Technical (Japanese fibre) | Standard | $21.99 | 4.3 | 1,298 | 1,794 | 1 |
| LUXEAR | Two-sided cooling / cotton | Standard | $16.95 | 4.2 | 6,708 | , | 3 |
| Elegear (silver) | Technical premium | Standard | $26.89 | 4.5 | 230 | about 1,010 | 8 |
| Beckham Hotel Collection | Technical nylon, envelope | King | $34.99 | 4.5 | 418 | , | 24 |
| REST Evercool+ | Premium | Standard | $59.25 to 79 | 4.4 | 1,208 | 5,078 to 5,738 | 24 |
| Bedsure (PureWoven) | Bamboo viscose | Queen | $12.99 | 4.4 | 37,479 | 19,630 | 17 (brand) |
| BEDELITE | Bamboo viscose | Queen | $8.49 | 4.4 | 12,229 | 21,407 | 1 |
| Bambaw | Bamboo viscose | Standard | $21.99 | 4.4 | 3,722 | , | 26 |
| TELUS | Bamboo rayon | King | $19.95 | 4.4 | 5,007 | 4,930 | , |
| Pure Bamboo | Bamboo viscose | Queen | $24.99 | 4.6 | 2,624 | , | 14 |
| Serta Power Chill | Protector | Std/Queen | $15.41 | 4.3 | 3,529 | 5,736 | 0 |
| Sleephoria (ours) | Technical knit, zipper | , | $20.99 to 23.99 | 4.5 | 464 | about 290 | , |

Source: live product pages checked to the exact child ASIN, 28 Sep 2026 (competitor analysis); estimated monthly sales from DataDive niche "Cooling PillowCases (Updated)", 28 Sep 2026 (order of magnitude). "Sponsored on" = Sponsored Products presence on 30 live searches.

What this table decides

- The market splits four ways: technical nylon (where CooLinens sits), bamboo viscose, premium, and protector or satin. The direct rivals are the technical-nylon listings at $13.99 to 21.99 with 672 to 3,862 reviews, Avolare, the Bedsure technical line, QUTOOL, Rifens, CHOSHOME and HOMFINE.

- CooLinens should compete on technical cooling plus the hidden zipper plus a matched size and value, not on generic "cooling" alone, where bamboo and mass-price listings dilute the auction.

- Elegear still shows that a $21 to 27 technology-claim pillowcase can sell about 1,000 a month on about 230 reviews; REST at $59 to 79 shows buyers pay for a fabric they trust. CooLinens prices under both at its holding price.

## 6.2 Who advertises

| Brand | Sponsored Products | Sponsored Brands | Brand video | Organic | Read |
| --- | --- | --- | --- | --- | --- |
| REST | 24 | 20 | 4 | 20 | Premium $59 to 79; SB on 20 of 30 queries incl. the head term |
| Bambaw | 26 | 1 | 3 | 20 | Bamboo viscose Standard $21.99; most frequent SP advertiser |
| Beckham Hotel Collection | 24 | 3 | 4 | 21 | King nylon $34.99, 418 reviews; SBV on our own brand query |
| Bedsure | 17 | 2 | 1 | 30 | Spans bamboo, technical and satin; organic on all 30 queries |
| Bella Coterie | 15 | 0 | 0 | 4 | Paid-led; little organic presence |
| DOZ | 14 | 0 | 0 | 2 | Bamboo viscose Queen $20; paid-led |
| Pure Bamboo | 14 | 0 | 0 | 8 | Queen $24.99, 4.6 stars; also advertises on our product page |
| Avolare | 12 | 3 | 0 | 25 | Nylon/spandex Queen $15.19 with hidden zipper, the closest product match |
| LOVSTOY | 12 | 0 | 0 | 0 | King $21.99; paid-only |
| Shunjie.Home | 9 | 0 | 0 | 4 | Bamboo Queen $13.29 |
| Elegear | 8 | 4 | 0 | 25 | Silver-infused Standard $26.89; advertises on our product page |
| Fittia | 5 | 3 | 0 | 7 | Zipper Standard $19.99 |
| Cozy Bliss | 2 | 0 | 9 | 16 | Video-led: SB Video on 9 of 30 queries |
| Rifens Home | 0 | 0 | 0 | 27 | Nylon Standard $18.98, 4.6 stars, organic-only, missing from the draft target list |
| BEDELITE | 1 | 0 | 0 | 25 | Mass price $8.49; organic-led |

Source: competitor analysis evidence workbook, Ad Presence Matrix, 30 live US searches (20 non-brand, 9 competitor-brand, 1 own-brand), one signed-out desktop session, 28 Sep 2026. Counts are searches where the format appeared: presence, not spend or impression share.

What this table decides

- The core auctions are crowded: REST, Bambaw and Beckham appear as sponsored results on 24 to 26 of 30 searches, Bedsure on 17, and REST adds brand banners on 20. This corrects version 1.0, which read "most competitors barely advertise" from DataDive keyword counts; the live panel is the better evidence.

- Some rivals are invisible to a Sponsored-Products-only scan: Rifens is organic-only on 27 of 30 searches, and Cozy Bliss runs brand video on 9 with Sponsored Products on 2.

- Our own pages are already contested. The "coolinens cooling pillowcase" search shows REST and Silvery banners and a Beckham video; our Queen page carries ads for Beckham, Elegear, Pure Bamboo, Bambaw and Gabire. That is the case for branded exact on day 1 and for Decision 7.

- Competitor CPCs, budgets and match types are private and cannot be read from public pages. The crowding raises the risk that real CPCs land above the seeds; the 12 Oct CPC-versus-seed read tests it before any money is added.

## 6.3 Competitor targeting, 16 targets

A target opens only when CooLinens wins at least two of price, rating and review count against it, at the size-matched price then live, or the target is out of stock. The draft listed 10 targets; the competitor analysis added six (Bedsure technical, QUTOOL, Rifens, LUXEAR, Beckham, Bambaw) and grouped all 16 into test pools A, B and C.

| Pool | Target (size) | Their price / rating / reviews | Our price at go-live, then at hold | Price | Rating | Reviews | Result at hold |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Avolare (Queen) | $15.19 / 4.4 / 3,862 | $17.99 to $21.99 | No | Yes | No | Not enterable |
| A | Bedsure technical (Queen) | $13.99 / 4.5 / 672 | $17.99 to $21.99 | No | Yes | No | Not enterable |
| A | QUTOOL (Queen) | $16.99 / 4.4 / 751 | $17.99 to $21.99 | Only at today's $15.99 | Yes | No | Not enterable |
| A | CHOSHOME (Standard) | $14.60 / 4.4 / 1,759 | $16.49 to $19.99 | No | Yes | No | Not enterable |
| A | HOMFINE (Standard) | $21.99 / 4.3 / 1,298 | $16.49 to $19.99 | Yes | Yes | No | Passes |
| A | Rifens Home (Standard) | $18.98 / 4.6 / 1,187 | $16.49 to $19.99 | Until the 28 Oct step | Yes | No | Window closes before Phase 3 |
| B | Elegear silver (Standard) | $26.89 / 4.5 / 230 | $16.49 to $19.99 | Yes | Yes | No (9 vs 230) | Passes |
| B | LUXEAR (Standard) | $16.95 / 4.2 / 6,708 | $16.49 to $19.99 | Until 14 Oct | Yes | No | Window closes before Phase 3 |
| B | REST (Standard) | $79 / 4.4 / 1,208 | $16.49 to $19.99 | Yes | Yes | No | Passes (premium test) |
| B | REST second colour (Standard) | $59.25 / 4.4 / 1,208 | $16.49 to $19.99 | Yes | Yes | No | Held: size to confirm |
| B | Beckham (King) | $34.99 / 4.5 / 418 | $18.99 to $23.99 | Yes | Yes | No | Passes (premium test) |
| C | Bedsure bamboo (Queen) | $12.99 / 4.4 / 37,479 | $17.99 to $21.99 | No | Yes | No | Not enterable |
| C | BEDELITE (Queen) | $8.49 / 4.4 / 12,229 | $17.99 to $21.99 | No | Yes | No | Not enterable |
| C | TELUS (King) | $19.95 / 4.4 / 5,007 | $18.99 to $23.99 | Until 14 Oct | Yes | No | Window closes before Phase 3 |
| C | Serta protector (Queen) | $15.41 / 4.3 / 3,529 | $17.99 to $21.99 | No | Yes | No | Not enterable |
| C | Bambaw (Standard) | $21.99 / 4.4 / 3,722 | $16.49 to $19.99 | Yes | Yes | No | Passes (adjacent material) |

Source: PAT Review tab (formulas on the Assumptions prices); target data from live product pages, 28 Sep 2026; pools from the competitor analysis.

What this table decides

- The 4.8 rating is the new win, it beats every target (4.2 to 4.6), and reviews lose to all 16. Price therefore decides: five targets pass durably at the holding price (HOMFINE, Elegear silver, REST, Beckham, Bambaw); the second REST listing is the same premium family and is held until its size conflict is checked. Rifens, LUXEAR, TELUS and QUTOOL pass only until an October price step.

- The rating rests on 9 ratings; one low review can take the rating axis away. It is re-read before the pool opens.

- Timing stays with the SOPs: conquest is a Phase 3 to 4 surface and needs stock green, so the five are prepared now and open at Phase 3 (mid December) with 100-click caps, bids seeded at expected CPC and never below the $0.50 floor. Premium (REST, Beckham) and adjacent-material (Bambaw) targets run as separate tests from the technical match (HOMFINE, Elegear), Decision 8.

## 6.4 Creative and conversion, how competitors sell, and our answer

| Competitor message | Who | CooLinens answer |
| --- | --- | --- |
| Heat relief first | REST ("Say goodbye to hot sweaty nights"); Avolare and Rifens: instant cool touch | Lead with the hot-sleeper problem and a touch and fit demonstration. Q-Max is a contact-cooling measure, not proof of all-night cooling |
| Secure fit | Avolare hidden zipper; Rifens fit praised in reviews; Beckham reviews mention slipping | Show the zipper closing, a movement test and full dimensions, our clearest point of difference against envelope closures |
| Beauty benefit | REST, Beckham, Rifens and the bamboo brands: silky feel, hair and skin | Show the smooth fabric; use substantiated low-friction wording, no medical or anti-acne claims |
| Technical premium | REST silver-infused yarn; Elegear silver upgrade; competing Q-Max figures | Do not invent a higher Q-Max, silver content, patent or certification; use verified documentation only |
| Trust and value | Rivals carry hundreds to thousands of reviews | Make "set of 2", size and care unmistakable; do not offset thin reviews with bigger promises |

A 15 to 25 second video to brief now, for Sponsored Brands video when it opens: 0 to 3 s a hot sleeper flips the pillow, then "Cooling pillowcases · Set of 2"; 3 to 10 s fabric touch, the hidden zipper closing, the exact size; 10 to 18 s movement and fit, simple wash care; close on a truthful value line in the matching colour and size. Test a cooling-first hook against a zipper-and-fit-first hook, with 10 to 15% of the envelope once the format opens.

# 7 Oversight: launch tracking

## 7.1 Dated checkpoints

| Date | What is judged | Against |
| --- | --- | --- |
| Daily from 30 Sep | Spend against envelope; delivery; Buy Box; stock by child | At most 110% of envelope; Buy Box at least 90%; no child under 21 days |
| 7 Oct (day 7) | Clicks against test pace; realised CPC against expected; placement split; budget in-day | At least 50% of pace; CPC within 25%; top of search carries most clicks; in-budget at least 70% |
| 14 Oct (day 14) | Head probe at 100 clicks; tests at 50 clicks; organic lift coefficient; second price step | Probe at least 15.7%, under 10%, or extend; 0 orders at 50 clicks stops a test |
| 28 Oct (day 28) | Tests at 100 clicks; Phase-2 entry; second read of organic lift; third price step | Conversion against plan and SQP market; data completeness at least 85% |
| 27 Nov to 11 Dec | Black Friday to Cyber Monday window | Event weeks and the 14 days after are excluded from trend verdicts; price steps held if a deal runs |
| 9 Dec and 23 Dec | Holding price reached (Queen and Standard, then King); conversion at the new price | Session conversion at least 12% |
| 11 Jan | Push release list against the conditions in 4.4 | Terms named, or a dated re-entry |

## 7.2 What the command center must track

The full 25-line specification (definition, source, cadence, target and the action each breach triggers) is in the Launch Tracking tab. The core lines:

| KPI | Source | Cadence | Target / trigger |
| --- | --- | --- | --- |
| Spend against envelope, in-budget % | ppc_daily, ppc_campaigns (product 70) | Daily | At most the envelope; in-budget under 70%, fix budget first |
| Clicks against cap per test; realised CPC against expected | ppc_keywords | Daily / weekly | Behind pace, one bid step of 15% to 25% |
| Placement split per test, from day 1 | ppc_keywords with placements, ppc_placements | Weekly | Verdicts on top-of-search clicks; top of search under 30%, fix placement first |
| Conversion per term (100 clicks) | ppc_keywords | Weekly | Below plan, listing fix before bids |
| Head-term probe | ppc_keywords (term, placements) | At 100 and 200 clicks | Rule in 4.7 |
| Expected CPC against max profitable CPC | Keyword Plan tab and ppc_keywords | Weekly | Above 1.5 outside a push, stop the term |
| Organic rank, 73 terms | DataDive rank tracker (to create) and ppc_ranks | Daily | Collapse above 10 places despite delivery, investigate, never add spend |
| Sessions and conversion by child | SellerBoard | Weekly | Under 12%, review before the next price step |
| Price gap against the actual 60-day average; Featured Offer | Business Reports, Pricing Health | Each move; daily for 7 days | Gap above 15%, halve the step; suppressed, revert the same day |
| Reviews displayed and rating, per routed child | Listing / Vine | Weekly | Displayed count reconciled with reported; rating at least 4.4 |
| Competitor ads on our product page and brand search | Weekly check | Weekly | Competitor banners on our brand search, raise branded defense one step |
| TACoS and weekly net after ads | ppc_summary; SellerBoard with COGS | Weekly | Net worse than minus $700/week, envelope review |
| Days of cover by child, projected | SellerBoard / DOH matrix | Daily | Yellow freezes push; red re-points the same day |
| Brand search, SQP share, seasonal index | SQP weekly | Weekly | Two rising weeks opens the push window |
| Sleephoria impact on shared terms | ppc_product_table; SellerBoard | Weekly | Both brands bidding the head term, escalate |
| Prediction scoring | Weekly change log | Weekly | Every action carries metric, direction, magnitude, horizon, review date |

## 7.3 Setup gaps to close before go-live

- Product 70 in the command center has no price, fee or landed cost, so it cannot show break-even ACoS or contribution for any SKU.

- SellerBoard shows $0 product cost for CooLinens for September; every profit figure there is overstated until COGS is loaded.

- There is no DataDive rank tracker and no ASINsight export for CooLinens; tracking must start on day 1.

- The parent ASIN must be confirmed once the variation merge completes; the command center currently points product 70 at the Blue King child.

- The Queen listing showed 9 reviews on 28 September against 125 reported; confirm the Vine reviews are attached to every child.

- Light Grey Standard stock is missing from the 28 September export (derived at 81 units, yellow).

- The MKL (10 Sep) needs a human relevancy stamp and a refresh before Phase 2.

# 8 Execution register

## 8.1 Wave one, with a prediction per action

| Action | Metric | Direction and size | Horizon | Review date | Reverses if |
| --- | --- | --- | --- | --- | --- |
| Ten exact tests, half base bid, top of search +100% | Clicks delivered per test | 100 clicks each within 28 days | 28 days | 28 Oct | Under 25 clicks by 7 Oct, one bid step up |
| Head-term probe | Top-of-search conversion on "cooling pillow cases" | At least 15.7% (Sleephoria's rate) | 14 days (28 if extended) | 14 Oct | Under 10%, Sleephoria keeps the term; 10% to 15.7%, extend to 200 |
| Placement ruling C1 | Top-of-search share of test clicks | Top of search carries most clicks | 7 days | 7 Oct | Under 30%, placement fix before any money is added |
| Branded exact at $0.50 | Brand clicks captured | At least 80% of brand-term clicks | 28 days | 28 Oct | A competitor ad above ours on brand terms, defensive step |
| Price step 1 (30 Sep) | Featured Offer and session conversion | Buy Box at least 90%; conversion at least 15% | 7 days | 7 Oct | Suppression, revert the same day |

## 8.2 Recommendations to Brand Management

- Price: approve the ladder, holding Queen $21.99 and Standard $19.99 from 9 December and King $23.99 from 23 December; set DTC and TikTok Shop prices at or above each Amazon step before it happens.

- Listing: resolve the main image before go-live and avoid text on the main image; Sleephoria's tagged main image got its listings suppressed in October 2025.

- Reviews: find out why the listing shows 9 reviews against 125 reported; track Vine claims to about 300 by mid-November; protect the 4.8 rating (it decides five competitor targets).

- Creative: brief the 15 to 25 second video in 6.4 now, and keep every claim to verified documentation.

- Unboxing: put the instruction card on top of the wrapping (a Sleephoria finding).

- Supply: place the reorder decision now; at a 200-day lead only 13.5 units a day stay green on current stock, and the push needs stock landing before the season peak.

- Cannibalisation: until December CooLinens sells at or below Sleephoria ($17.99 to $20.99 against $21.99); watch Sleephoria's sales and hold its price.

## 8.3 Expected outcome

| Measure | Draft workbook | This plan, Phase 1 | This plan, push window |
| --- | --- | --- | --- |
| Daily spend | $1,635 | $103 | Ceiling $538; release list from observed results |
| Ad orders/day | 87 target | About 6 | About 34 at the full ceiling |
| Units/day incl. organic | About 89 | About 9.9 | About 36 |
| Stock runway | 34 days | 302 days at this pace | 83 days without a reorder |
| Contribution per Queen unit | $1.63 to $4.31 basis | $6.01 rising to $9.41 | $9.41 at hold |
| Net after ads | Not stated | About minus $44/day (minus $311/week), narrowing each step | Loss ceiling written per push |
| Evidence produced | Rank targets 3 to 7 on 73 keywords | A 100-click read on 10 intents; head-term ownership | Rank at target, stable two weeks |

# 9 Reconciliation, gaps, risks and decisions

## 9.1 Figures reconciled with the workbook

Every headline figure in this document is computed in the companion workbook, and its Cross-check tab matches all 27 headline values: Phase-1 envelope $102.86 ($107.86 with Decision 7); 10 tests, 12 Phase-2 exact, 27 tail, 23 discovery and 1 excluded; 39.3 clicks and 6.05 ad orders a day; 302 days of runway; net minus $311 a week; push ceiling $537.79 ($349.25 at 24%, $294.61 on SQP) and 83 days of runway; head term 12 sales and $211.22 a day (5 and $88.01 on SQP); draft $1,634.90 and 34 days; Option B $368.67 and minus $1,249 a week; stock 2,981; sibling share 92% and 43%; five passing competitor targets. The workbook recalculates with zero formula errors, and every driver in the Keyword Plan is a formula on the Assumptions tab. Every change from the draft, from version 1.0 and from version 1.1 is listed in its Change Review tab with a reviewer mark column.

## 9.2 Named gaps

| Gap | What it blocks | Owner | Due |
| --- | --- | --- | --- |
| COGS unconfirmed for both pillowcase brands | Every ceiling is provisional; Phase 2 cannot open | Finance / Data | Before go-live |
| Reorder lead time and quantity unknown | How hard the February push can run | Supply Chain | 9 Oct |
| Parent ASIN not yet assigned | Command-center tracking at parent level | Brand Management | At merge |
| 9 reviews displayed against 125 reported | Review risk and the competitor entry test | Brand Management | Before go-live |
| Market level for sales targets (Data Rova 143 a day against SQP 55.6 on the head term) | The push budget is a range until the probe reads | PPC Lead | 14 Oct |
| Competitor CPCs, budgets and match types | Private; cannot be read from public pages; CPC risk tested on our own reads | PPC | 7 Oct read |
| No rank tracker for CooLinens | Every rank verdict until one month of history | PPC | Before go-live |
| Placement feed recorded as missing | Placement reads for ruling C1 | Data | Before go-live |

## 9.3 What the data could not show

- Conversion above $23 on this knit: Sleephoria never sold there, so every figure at the holding price and above is modelled, not measured.

- CooLinens' own CPC and conversion: none exist until go-live; the tests exist to replace the borrowed figures within four weeks.

- The organic lift per ad order (0.3) is a soft coefficient; it is measured on 14 and 28 October and resizes every runway figure.

- What competitors pay: the live search panel shows who appears, from one session, not their spend or impression share.

## 9.4 Risks and what would falsify this plan

| Risk | Falsified if | Checked on |
| --- | --- | --- |
| CooLinens converts well below Sleephoria at launch prices | Probe under 10% at 100 clicks, or the average test under 8% | 14 and 28 Oct |
| The auction is dearer than Sleephoria's history (REST, Bambaw, Beckham on 24 to 26 of 30 searches) | Realised CPC above 1.5 times expected on at least 4 tests | 7 Oct |
| Price steps trip Buy Box suppression | Featured Offer lost after a step | 2 to 4 hours after each step |
| Conversion does not hold as price rises | Session conversion under 12% after the 9 Dec step | 16 Dec |
| The 4.8 rating slips | Rating under 4.6 before Phase 3 | Weekly |
| The season turns late | No two rising weeks by 15 Feb | 15 Feb |
| Confirmed COGS is higher than the rebased figure | Contribution falls; ceilings shrink one for one | On confirmation |

## 9.5 Decisions requested

| # | Decision | Figures | What follows from each answer | Owner |
| --- | --- | --- | --- | --- |
| 1 | Envelope: Option A, B, C or D | A $103/day; B $369/day, minus $1,249/week; C $1,635/day, stock out about 2 Nov; D $120/day for 7 days | A: build the ten tests for 30 Sep. B: needs a below-break-even approval with an end date. C: not recommended. D: needs an override for competitor targeting and discovery in Phase 1 | Brand owner |
| 2 | ACoS rule for ranking spend | 1.5 times break-even ACoS at the price live during the push, inside the 50% to 80% band; Queen at $21.99 = 64% | Confirmed: written into every push sizing. Changed: pushes re-sized before release | Brand owner |
| 3 | Reorder | Green holds only up to 13.5 units/day at a 200-day lead; the push ceiling runs 36 a day | Placed with a date: the February push is sized to it. Not placed: the push runs only on terms the stock can carry | Supply Chain / Brand owner |
| 4 | Head-term ownership | Composite 92% to 43% CooLinens depending on the depth read | Declared after the probe (14 to 28 Oct): the other brand walls the term the same day | PPC Lead, reviewed by Brand Management |
| 5 | Price ladder and holding price | Q $17.99 to $21.99 by 9 Dec; S $16.49 to $19.99 by 9 Dec; K $18.99 to $23.99 by 23 Dec | Approved: first step on 30 Sep with go-live. Not: every ceiling stays at live-price economics | Brand Management |
| 6 | COGS confirmation | Rebased COGS K $4.70, Q $4.06, S $3.86 unconfirmed | Confirmed before go-live: ceilings final. Late: Phase 2 slips | Finance / Data |
| 7 | Own-ASIN self-targeting from go-live | $0.50 floor, $5/day (envelope $108/day). Five brands already advertise on our Queen page | Approved: a defensive exception to the exact-only Phase 1, logged as such. Not: opens at Phase 2 (28 Oct) | PPC Lead |
| 8 | First competitor-targeting pool | Five pass at hold: HOMFINE, Elegear silver, REST, Beckham, Bambaw; second REST listing held | Approved: opens at Phase 3 with 100-click caps; premium and adjacent-material targets tested separately. Not: re-tested from scratch at Phase 3 | PPC Lead |

## 9.6 Rulings of 29 September

| # | Question | Ruling | Consequence in this plan |
| --- | --- | --- | --- |
| C1 | Placement at entry: SOP-22 zero modifiers, or the top-of-search entry model accepted on the Cooling Fitted Sheet | Base bid half the expected CPC with a 100% top-of-search modifier; conversion read by placement from day 1 | The effective top-of-search bid equals the expected CPC; the probe and tests are judged on top-of-search clicks. Logged as a deviation from SOP-22 |
| C2 | Market level for the daily sales targets | The brand owner's 15 September basis governs; SQP measured purchases are the low case | Head term 12 a day ($211) against 5 ($88); push ceiling $538 against $295 |
| C3 | Planning conversion | Sleephoria pooled 15.6% as the base; 24% launch-month rate as a sensitivity | Bands and push budgets shown both ways and labelled provisional until the 100-click reads |
| C4 | Review gate | Observed-results test decides the push; review count is a risk note per term | The February release list is named on 11 January from test results; SOP-23 family F4 flagged for amendment |
| C7 | Go-live date | 30 September, from the launch channel of 29 September | Every date re-based; the workbook recalculates from one go-live cell if the date moves |

## Sources

- Launch channel #coolinens-cooling-pillowcase (10 to 29 Sep 2026) and sister channel #cooling-pillowcases (Nov 2024 to Sep 2026), including the launch brief, Buy Box safety standard, COGS sheets, creator sample list and the Sleephoria PPC plan (10 Sep).

- Draft launch workbook COOLINENS_Cooling_Pillowcases_2_Piece.xlsx (29 Sep 2026), including its MKL Data Rova and click-share columns.

- USA cooling pillowcases competitor and PPC strategy analysis and its evidence workbook (28 Sep 2026).

- Review of the PPC Launch Strategy v1.1 and Launch Workbook v1.1: corrections register and reviewer opinion (29 Sep 2026).

- SellerBoard (Ecotero account): CooLinens 1 to 28 Sep 2026 by SKU; Sleephoria monthly Oct 2025 to Sep 2026.

- Ecotero command center: product table, keyword performance for product 43, product context for products 43 and 70, ASINsight export for product 43.

- DataDive: niche "Cooling PillowCases (Updated)" competitors and keyword rank grid (28 Sep 2026); Sleephoria rank radar with SQP (1 Jul to 28 Sep 2026).

- PPC SOPs in the PPC-Audit repository: 06, 12, 15, 16, 22, 23, 28, 30, 33, 41; config/thresholds.yml.